# PROJECT SAMANTHA

# MACHINE LOADING SHOP FLOOR

# DETAILED PLAN - Every phase, every task, every deliverable:

Phase 0 — Foundation (Week 1)

Goal: data pipeline working end-to-end before any ML code is written.

Tasks: create the exact folder structure from CLAUDE.md, initialise Python venv and install all dependencies (fastapi uvicorn ortools pandas python-oracledb python-dotenv), write db.py with a connection pool using oracledb.create_pool() in thin mode, write SELECT helpers for all 4 read-only Oracle tables with correct dtype casting (dates → datetime, numerics → float), write preprocess.py with resolve_capacity() and clean_wip_orders() (filters rework, assigns priority 0 for null PDD), verify schedule_output and sim_results tables exist in Oracle with correct column schemas, write a test_connection.py script that reads all 4 tables and prints resolved capacity for the next 7 days, and confirm zero errors.

Deliverables: db.py, preprocess.py, .env template, .gitignore, requirements.txt, passing test script.

Phase 1 — Engine 1: CP-SAT scheduler (Weeks 2 - 3)

Goal: engine1_scheduler.py reads live Oracle data, solves the scheduling problem, writes a complete Gantt plan to schedule_output.

Week 2 — model structure: define CP-SAT IntervalVar for each (serial, operation) pair, add precedence constraints enforcing Op10 → Op20 → Op30 → Op40 → Op50 → Op60 → Op80 → Op90 → Op100 → Op110 per serial, add no-overlap constraints per machine per shift, add capacity constraints using capacity_resolved.available_time_min per machine+shift+date, implement the P1/P2 machine selection fallback logic.

Week 3 — objective and output: compute urgency_weight for every order using pdd_score + ageing_score + batch_bonus, set urgency = 0 for null-PDD safety stock orders, set up the cp_model.Minimize() weighted tardiness objective, test on a realistic WIP subset, write output rows to schedule_output with run_id = uuid4() and generated_at = now().

Deliverables: engine1_scheduler.py, unit test confirming valid sequence output with no capacity violations.

Phase 2 — Engine 2: Recommendation engine (Week 4)

Goal: engine2_recommender.py accepts order IDs, simulates the priority change, writes risk report to sim_results.

Week 4: snapshot current schedule_output by run_id into a baseline dict, set elevated order urgency_weight = 999999 by overriding its entry in the solver input, re-run CP-SAT with a strict 10-second parameters.max_time_in_seconds = 10 limit, extract new_completion_date as max(scheduled_date) over all serials for each order's final operation.

Week 5: compute slip_days for every non-elevated order, compute slack = PDD − new_completion_date, classify SAFE / AT_RISK / BREACH, sort by absolute slip descending, write all rows to sim_results with a sim_id, return the top-5 most impacted orders.

Deliverables: engine2_recommender.py, test confirming correct risk classification against a known scenario.

Phase 3 — FastAPI endpoints (Weeks 5 - 6)

Goal: all 6 endpoints working, documented, CORS-enabled, with proper error handling.

POST /schedule/generate: calls Engine 1, returns {"run_id": "...", "status": "ok", "orders_scheduled": N}. GET /schedule/current: reads latest run_id from schedule_output, returns Gantt-ready JSON grouped by {machine_name: [{date, shift, orders: [...]}]}. POST /priority/simulate: accepts {"orders": ["VL1000551"]}, calls Engine 2, returns top-5 impact rows. GET /orders/wip: returns all active non-rework orders with current op status. GET /machines/capacity: accepts query param days=7, returns capacity_resolved for the next N dates. POST /data/refresh: re-runs all 4 Oracle SELECTs and reloads in-memory state, returns row counts.

Write models.py with Pydantic request/response schemas for all endpoints. Add HTTPException handling for Oracle connection failures. Add CORS middleware allowing the React origin. Confirm Swagger UI at http://localhost:8000/docs.

Deliverables: main.py, models.py, all 6 endpoints tested with curl or Postman.

Phase 4 — React frontend (Weeks 7–8)

Goal: three views connected to the live FastAPI backend, production-quality UI.

api/client.js: a single module exporting all fetch functions with a configurable API_BASE_URL (reads from import.meta.env.VITE_API_URL, defaults to empty string so Vite proxy handles it in dev).

ScheduleView.jsx: Gantt chart using Recharts BarChart with one row per machine, bars representing operations coloured by utilisation percentage (green under 70%, amber 70–90%, red over 90%). "Generate Schedule" button triggers POST /schedule/generate with a loading spinner. "Refresh Data" button triggers POST /data/refresh.

OrderBoard.jsx: WIP order cards using React DnD for drag-to-reprioritise into a priority queue column. Each card shows order ID, size/class/design/MOC, current operation, PDD, and urgency badge. "Simulate Impact" button sends selected orders to POST /priority/simulate.

ImpactAnalyser.jsx: risk report table with columns for order ID, current PDD, old completion, new completion, slip days, and RiskBadge.jsx component (green SAFE, amber AT_RISK, red BREACH). Wire Vite proxy in vite.config.js.

Deliverables: all three views functional, full round-trip from UI to Oracle write to result displayed.

Phase 5 — Production deployment on Windows Server (Week 9)

Goal: application permanently running on the company server, accessible from any browser on the company network.

Backend: copy project to server, install Python 3.11, install all pip dependencies in a venv, create .env with production Oracle credentials, register Uvicorn as a Windows Service: nssm install TovMLO-API "C:\path\venv\Scripts\uvicorn.exe" "main:app --host 0.0.0.0 --port 8000", set working directory to backend/, start service.

Frontend: run npm run build to generate /dist, create server.js (Express serving /dist + proxying /api/* to localhost:8000), register Express as a Windows Service: nssm install TovMLO-Frontend "C:\path\node.exe" "server.js", start service on port 80. Verify: open http://server-ip in a browser, confirm React app loads, hit "Generate Schedule", confirm Gantt renders with real Oracle data, drag an order card, confirm risk report populates with correct breach flags.